## ProjectPlan
PLAN_CODE | PLAN_NAME | MO_ID | OPERATION_SEQUENCE | OPERATION_NAME | WORK_CENTER_CODE | START_HOUR | DURATION_HOURS | STATUS | NOTES
PLAN-STARTRANS-W12 | Star Trans Week 12 Production | MO-ST-001 | 10 | Wind LV/HV Coils | WC002 | 0 | 1.5 | planned | Copper expedite lane
PLAN-STARTRANS-W12 | Star Trans Week 12 Production | MO-ST-001 | 20 | Core & Coil Assembly | WC001 | 1.5 | 2 | planned | Great Lakes Utility order
PLAN-STARTRANS-W12 | Star Trans Week 12 Production | MO-ST-001 | 30 | Tank Fit-Up & Vacuum Test | WC003 | 3.5 | 0.75 | planned | FPY checkpoint
PLAN-STARTRANS-W12 | Star Trans Week 12 Production | MO-ST-005 | 10 | Fabricate Pad-Mount Tank | WC002 | 2.5 | 2.5 | frozen | Pad-mount batch